Project Planning - Checklist

[In columns "inputs" and "results", we show elements we think that are absolutely necessary; please adapt or extend to your specific project needs.]

| # | Item | Inputs | Results [and Remarks] |
| --- | --- | --- | --- |
| 1 | Project Goal / Vision | problem that has to be solved; idea of creating a new product or service; ...; | SMART wording of a project goal [in case of an anticipated customer-contractor relationship, communication between customer and contractor of most results of project definition and planning will start, as early as now, in general, as early as possible] |
| 2 | Project Charter | project goal | text-based project charter [during project definition and planning phase, this is a living document, to be updated virtually permanently] |
| 3 | Project Management Handbook | project goal | text-based project management handbook [during project definition and planning phase, this is a living document, to be updated virtually permanently] |
| 4 | Stakeholder Management Plan | project goal; relationship to known or presumable stakeholders | graphical, text- or worksheet-based representation of stakeholder management plan, including action plan for resolving conflicting interests |
| 5 | Expected Project Results | project goal | description of expected results |
| 6 | Requirements / Specifications (technical, services, contractual | expected project results; standards, rules, regulations; law (codified or cases); best practice examples; external feasibility studies | description of requirements / specifications of project results, as detailed as possible |
| 7 | Product Breakdown Structure (PBS) | requirements / specifications | graphical and text-based representation of PBS |
| 8 | Work Breakdown Structure (WBS) | PBS | graphical and text-based representation of WBS, detailed down to the level of work packages (WP's) |
| 9 | Effort Estimation | WBS, expertise, data of earlier similar projects | estimates of best-normal-worst case effort, duration, human resources (level of skills), tools, material, cost per WP |
| 10 | Project Selection; Project Prioritization | WBS; effort estimation | input data for project selection and / or prioritization |
| 11 | Risk Analysis | WBS, first round of effort estimation, expertise, data of earlier similar projects | risk list; eventually additional WP's, project contingency, i.e. revised WBS and cost per WP |
| 12 | Milestone Plan | WBS, effort estimation, risk analysis | project milestone plan |
| 13 | Network Diagram | WBS, effort estimation, risk analysis; milestone plan; expertise | graphical representation of network diagram, the logical sequence of all WP's, including milestones |
| 14 | Gantt Chart | WBS; milestone plan; network diagram | graphical representation of Gantt chart |
| 15 | Assignment of Resources | WBS; milestone plan; network diagram; Gantt chart | committed resources, including results of negotiations with suppliers or sub-suppliers: legally binding proposals or contracts with suppliers or sub-suppliers |
| 16 | Resource Plan | committed resources | resource plan, including start and end dates of all assignments on this project; cost of resources |
| 17 | Cost Plan | resource plan | graphical and worksheet representation of accumulated cost plan |
| 18 | Payment Plan | cost plan | graphical and worksheet representation of payment plan, sales plan (in case the project is about creating a new product), or financing plan [in case of a customer-contractor relationship, this step goes along with contract negotiations between customer and contractor, at the latest] |
| 18 | Communications Plan | all earlier planning documents | graphical and text-based representation of the communications plan |
| 19 | Controlling Tools | all earlier planning documents | setup of controlling tools, including reporting system, project management dashboard, plan of status meetings, control board or other review meetings, risk management workshops |
| 20 | Contract Management | all earlier planning documents; applicable law | signed contract between project owner (customer) and supplier (contractor), including detailed contractual wording of project scope, schedule, and payment; communications plan; risk management approach; change process; claim process; acceptance procedures; terms and conditions |
| 21 | Project Termination Criteria | all earlier planning documents; contract | clear criteria based on which the project shall be terminated, i.e. directly transferred to project closure procedures |